## Main
a | Today | Copy this doc and follow the link below for instructions. |  |  | 59 | 17 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2017-04-03 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-20 | 2017-03-21 | 2017-03-22 | 2017-03-23 | 2017-03-24 | 2017-03-25 | 2017-03-26 | 2017-03-27 | 2017-03-28 | 2017-03-29 | 2017-03-30 | 2017-03-31 | 2017-04-01 | 2017-04-02 | 2017-04-03 | Detailed Information | Status
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
5 | 1 | Remainder of ships do not fall after core is destroyed | JF |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Just blow everything up at the end. | Assigned
7 | 1 | Players can duplicate and steal each others' items | JF |  | 1 | 0 | 0.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Disable colliders of held items | Verify?
9 | 2 | New font in menu is fuzzy | JF |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Import fonts as large size (300+) and Unicode for best results | Deferred
8 | 1 | Player cannot fire without aiming right stick; should be able to fire in current position of gun | AW |  | 1 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 |  | Fixed
8 | 2 | Valid block placement spaces get messed up when swapping blocks around during build |  |  | 1 | 1 | 0 |  | 1 | [16 empty] | Fixed | bar: 2017-03-20 to 2017-04-03
8 | 2 | Players can always jump when contacting the little block dispenser platforms (Ground layer) |  |  | 1 | 1 | 0 |  | 1 | [16 empty] | Fixed | bar: 2017-03-20 to 2017-04-03
Comments from Playtesting | [25 empty] | Reported
11 |  | Blocks were hard to pickup (too small) | [23 empty] | Can't Repro
12 |  | Hard to see when holding a block
13 |  | Didn't feel like much strategic choice after the 2nd play (just build out on the same level as the core and press X as fast as you can)
14 |  | Confusing ending (once their core was destroyed they could still jump around and invade the other persons ship)
15 |  | Suggestion from playtester: Add a charged weapon or different weapon (I think the motivation for this was to prevent a bullet clustertruck, just a cooldown might suffice?)
16 | 1 | Add player respawn | SK |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  | CG: Almost no one used all of the controls/were still confused even with the tooltips. Need to guide the player better (tutorial?)
19 | 1 | Solidify win condition (so game actually ends) | SK |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Players can still jump around and drive their ship even though it displays what team wins. Some testers didn't feel this was an actual end to the game that they were expecting
21
22
Player | [25 empty] | Reported
24 | 1 | Increase and tune player projectile speed | JF |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Increased projectile speed to 20, nerfed damage per shot to 7, implemented triple shot
25 | 1 | Change layering settings to allow players to land on each others' ships | JF |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 4 | Player knockback when hit by laser while not standing on own ship | SK |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | This is pretty much already done with the implementation of triple shot
27 | 1 | Make it so right stick aims and shoots simultaneously | CG |  | 1 | 0 | 0.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | These changes are on the "experimental" branch in git
28 | 1 | Only be able to place block in front of the player (experimental) | CG |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | These changes are on the "strict-placement-experiment" branch in git
29 | 2 | Player respawn UFO animations |  |  | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
29 | 2 | Player piloting and hurt animations | JF |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Environment | [25 empty] | Reported
37 | 4 | Sprite up ground and some sort of thematic middle divider (a command building or something) | JF | AW | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0
38 | 2 | Sound Effects System | AW | JF | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | See Justin for update to AudioSource on MainCamera
39 | 5 | Space base background? | JF |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
40 | 1 | Expand rocket platform to five wide | CG |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 1 | Make core look like a ship's bridge that you can drive | CG | JF | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
28 | 3 | Block spriting upgrade for clearer differentiation | JF |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
37 | 4 | Create rocket powered flying billboard to display coins and phase information |  |  | 2 | 2 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
37 | 1 | Redefine outer walls during phases | AW |  | 2 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
42
Experiments | [25 empty] | Reported
44 | 1 | Make it so you can pick up a resource and use as much of that resource (while still being charged for the cost of it) as you'd like | CG |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | On master branch
46 | 1 | Allow players to swap blocks with any other block on ship including core | JF |  | 3 | 0 | 4 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
49 | 3 | Battle phase camera tweaks and screen shake on liftoff | CG |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | on master
50 | 1 | Repair damaged blocks during battle phase with X (core unreparable) | SK |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 2 | Explosion physics and animations for all destroyed blocks, core, and engines | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
51 | 1 | Place blocks by aiming right joystick + Right Trigger | CG |  | 1.5 | 0 | 2 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | These changes are on the "experimental" branch in git
53 | 2 | Veering mechanic depending on how off-balanced ship blocks are |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Remove or move out walls during battle, but restrict Cores within camera
53 | 2 | Deal damage to core if on edge of screen |  |  | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | Remove or move out walls during battle, but restrict Cores within camera
55 | 2 | Buff piloting speed, tune masses of blocks to make tankier ships harder to pilot |  |  | 1 | 1 |  |  | 1 | bar: 2017-03-20 to 2017-04-03
56
Guiding the Player | [25 empty] | Reported
20 | 1 | Update Menu to lead to Tutorial | AW |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
52 | 2 | Revamp player build guidance; highlight all available spaces when holding, move item sprite + indicator around to aim | CG |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | These changes are on the "experimental" branch in git
18 | 1 | Tutorial on how to use controls | AW |  | 4 | 0 | 6 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
29 | 2 | Repair tooltip prompt when player moves near damaged block |  |  | 1 | 1 |  |  | 1 | bar: 2017-03-20 to 2017-04-03
28 | 3 | Repair animation, puff of smoke or wrench or something that pops up when repair is performed |  |  | 1 | 1 |  |  | 1 | bar: 2017-03-20 to 2017-04-03
63 | 2 | Associate team colors with jetpacks, guns, rockets, projectiles, etc. | JF |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
64 | 2 | Default weapons to aim downwards toward middle of view when starting battle phase |  |  | 1 | 1 |  |  | 1 | bar: 2017-03-20 to 2017-04-03
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 59 | 59 | 54.7857 | 50.5714 | 46.3571 | 42.1429 | 37.9286 | 33.7143 | 29.5 | 25.2857 | 21.0714 | 16.8571 | 12.6429 | 8.4286 | 4.2143 | 0
212
213 |  | Sum | [6 empty] | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 19 | 13 | 11 | 6 | 6 | 0 | 0 | 0
216 |  |  | 2 | [5 empty] | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 21.5 | 18.5 | 18.5 | 15.5 | 14 | 12 | 12 | 12
217 |  |  | 3 | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1
218 |  |  | 4 | [5 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 4 | 4
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Alexander Wang | AW |  |  |  |  | AW | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 9 | 5 | 5 | 0 | 0 | 0
223 |  | Stephen Kline | SK |  |  |  |  | SK | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2
224 |  | Justin Fan | JF |  |  |  |  | JF | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 16.5 | 14.5 | 11.5 | 11.5 | 6.5 | 5 | 2 | 0 | 0
225 |  | Cameron Gagnon | CG |  |  |  |  | CG | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59 | 59
236

## Daily Scrum
Producer | 2017-04-03 |  | Team Members
Approved | Dates |  | Alexander Wang | Stephen Kline | Justin Fan | Cameron Gagnon | All
| 2017-03-20 | Mon |  | Done: Turned 22 Next: Playtest game Help: — | Done: Next: Help:
| 2017-03-21 | Tue | Done: Bug fixed collisions; Update menu design; Submitted music collab doc Next: Implement Tutorial Help: — | Done: Tested game Next: N/A Help: — | Done: See All Next: Cause rockets to fall after destruction Help: |  | Done: Platform Effector collision bugfix, playtesting, playtesting for Group 5 Next: Third-party playtesting for both ours and Group 5
| 2017-03-22 | Wed
| 2017-03-23 | Thu |  |  | Done: Updated planning document and kanban with proposed changes based off feedback Next: Don't know yet Help: Start picking up tasks
| 2017-03-24 | Fri |  | Done: Updated burndown Next: Evaulate playtest results Help: — | Done: Updated burndown and planning Next: Moveable core, rocket/core relationship Help: What even are weekends
| 2017-03-25 | Sat |  |  |  | Done: Playtest other groups game at MHacks Next: --- Help: —
| 2017-03-26 | Sun | Done: Some of the tutorial Next: More tutorial Help: — |  |  | Done: write executive summary for playtesting other groups game Next: work on own game Help: —
| 2017-03-27 | Mon | Done: Half o the tutorial Next: Playtested; Rest of fhe tutorial Help: — | Done: Met with partner group to discuss playtest findings Next: Add player respawns and win ending game Help: — |  | Done: Prototyping shooting controls and being able to place as many blocks as resources will allow Next: Guide player when placing blocks (highlight available places) Help: —
| 2017-03-28 | Tue |  | Done: Player respawns and end-game condition Next: Repairable blocks Help: — | Done: Rocket base explosion update, burst fire, 5-second respawn timer Next: Movable core Help: Input situation | Done: Show highlight around blocks. Begin adding incontrol support. Next: Tweaks and finishing beta features Help: — | Done: Experiment with different control schemes, implemented InControl support Next: Beta features Help:
| 2017-03-29 | Wed | Done: Finished Tutorial Next: --- Help: —
| 2017-03-30 | Thu |  | Done: Brainstorming, repairable blocks Next: N/A (gone all weekend) Help: --- | Done: A E S T H E T I C, bugfixes, tweaks, brainstorming Next: Moveable core, minor tweaks to character sprites Help:
| 2017-03-31 | Fri | Done: Updated UI and fixed tweaked misc. features Next: Update UI and Setup playtest details Help: — |  | Done: Character sprites for Jetpack/Piloting/Hurt, tweaks and bugfixes Next: Moveable core Help: Playtesting changes, 1s and 2s on board
| 2017-04-01 | Sat | Done: Created new playtest survey; SFX System Next: Create playtest script Help: —
| 2017-04-02 | Sun | Done: Updated playtest script Next: N/A Help: — | Done: Justification doc Next: -- Help: -- | Done: Block swapping prototype Next: Bugfixes, aesthetic upgrades, experimental features Help: Submit beta | Done: Justification doc. Small block placement bugfix. Tweak aesthetic of resource points Next: --- Help: —
| 2017-04-03 | Mon
| 2017-04-04 | Tue
| 2017-04-05 | Wed
| 2017-04-06 | Thu
| 2017-04-07 | Fri
| 2017-04-08 | Sat
| 2017-04-09 | Sun
| 2017-04-10 | Mon