## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 63.1 | 0 |  |  |  | 17 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 2
| 2017-04-21 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Thu | Fri | Sat | Sun | Mon | Tue | Thu | Fri | Sat | Sun | Mon | Tue | Thu | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-04-03 | 2017-04-04 | 2017-04-06 | 2017-04-07 | 2017-04-08 | 2017-04-09 | 2017-04-10 | 2017-04-11 | 2017-04-13 | 2017-04-14 | 2017-04-15 | 2017-04-16 | 2017-04-17 | 2017-04-18 | 2017-04-20 | Detailed Information | Status
Guiding the Player | [25 empty] | Reported
1 | 2 | Improve Tutorial Battle Controls Screen | CG | JF | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Add another ship to shoot at and pilot | Fixed
2 | 1 | Player Select | AW |  | 3 | 0 | 4 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
3 | 1 | Team Select | AW |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
4 | 1 | Make Tutorial UI more clear | CG | JF | 1 | 0 | 7 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
5 | 1 | Connect menu selections to game settings | AW |  | 3 | 0 | 5 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
6 | 1 | Show arrow when Player is off the screen | CG |  | 2 | 0 | 4 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | It's easy for players to get lost when they fly off the screen. Have an arrow showing where they are (like smash) to get them back on
7 | 1 | Large Core Health bars replace Money during Battle | CG |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 |  | Fixed
8 | 1 | Arrow to show player location | AW |  | 2 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 |  | Fixed
9 | 1 | Add freeze frames to tutorial highlighting the block spawners and battle phase controls/piloting | AW |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 |  | Fixed
10 | 1 | New sprite for explosive block | CG | JF | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Juicy Juice - All Natural 100% Juice | [25 empty] | Reported
11 | 2 | Respawn in UFOs | CG |  | 3 | 0 | 3 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
12 | 2 | Camera Zooms out with Rockets | SK |  | 2 | 0 | 3 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 3 | Players enter game on UFO | CG |  | 2 | 0 | 0.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | Add Jiggly Jiggle Jello Mode | CG |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Add the setting on the menu confirm page and update GameManager
15 | 3 | Visible block damage sprites | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
16 | 1 | Buy Juice Boxes for Expo | ALL |  | 1 | 0 | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | The trigger word is any variation of "not enough juice"
17 | 1 | Explosion sound effects | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | The trigger word is any variation of "not enough juice"
Mechanic Tweaks | [25 empty] | Reported
18 | 2 | Hold X to drive the ship and release X to exit | CG |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Per Austin's comment in class.
19 | 1 | Recharge jetpack when player falls off screen | CG |  | 0.5 | 0 | 0.15 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | Move RB funcs to A. Remove aiming of blocks | AW |  | 0.5 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
21 | 1 | Don't allow players to shoot through their own ship | CG |  | 0.1 | 0 | 0.05 |  | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0 | 0 | 0
Experimental Features (Add Sparingly) | [25 empty] | Reported
22 | 2 | Slow-Mo for core being destroyed | CG |  | 1.5 | 0 | 4 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Toss in some camera zoom and screen for extra juice
23 | 1 | Prevent players from entering opposing team's blocks | CG |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | Explosive blocks | JF | CG | 2 | 0 | 3.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | As suggested in the feedback for beta, the staff would like to see some offensive blocks to spice up offensive attacks
25 | 1 | Block Ramming Mechanic | JF | CG | 2 | 0 | 3.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 0 | 0
26 | 1 | Reflective Blocks | JF |  | 2 | 0 | 0 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Documentation and Logistics | [25 empty] | Reported
27 | 1 | Trailer Video | SK |  | 4 | 0 | 4 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
28 | 3 | Justin-ification Doc | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
29 | 1 | Re-do trailer | SK |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
30
Bug Fixes | [25 empty] | Reported
31 | 1 | Players keep falling through rocket after respawning | CG |  | 2 | 0 | 1 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I think players might have somehow fallen through the platform they're standing on, and when they respawn the same keeps happening. Making their gravity set to 0 when driving seemed to fix it. I was at a point where I could almost reliably trigger the bug and after changing the gravity, it didn't seem to happen
32 | 1 | Background is messed up when zooming | CG |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | Fixed
33 | 2 | Line up timer with countdown when both teams use up all their money | CG |  | 0.5 | 0 | 0.15 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Fixed
34 |  | placing gameobjects on screen causes some to be shifted around and not display properly on top of the piloting position | [23 empty] | Cannot Reproduce
35 | 2 | Make offscreen indicators disappear for end of tutorial battle phase | CG |  | 0.5 | 0 | 1 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Fixed
36 | 3 | Detaching and Reattaching Controller Duplicated player | AW |  | 0.5 | 0 | 0 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Fixed
37 | 2 | Exploding blocks sometimes still deal damage to their own teams blocks. | CG |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Only sometimes do exploding blocks deal damage to their own team. It's not clear yet what conditions lead to this circumstance, but it happens. | Fixed
38 | 2 | Can't do successive jelly mdoes | CG |  | 0.5 | 0 | 0.15 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Fixed
39 | 1 | Players can down jump through middle or outer walls | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 |  | Fixed
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 17 | 17 | 16 | 14 | 13 | 12 | 11 | 10 | 9 | 7 | 6 | 5 | 4 | 3 | 2 | 0
211 |  | Optimum | [5 empty] | Line | 63.1 | 63.1 | 59.3882 | 51.9647 | 48.2529 | 44.5412 | 40.8294 | 37.1176 | 33.4059 | 25.9824 | 22.2706 | 18.5588 | 14.8471 | 11.1353 | 7.4235 | 0
212
213 |  | Sum | [6 empty] | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1 | 59.1
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 42.1 | 40.1 | 37.1 | 34.1 | 34.1 | 34.1 | 34.1 | 34.1 | 30.1 | 27.6 | 27.6 | 24.6 | 19.6 | 11.5 | 6 | 0
216 |  |  | 2 | [5 empty] | 14.5 | 12.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9 | 7.5 | 5.5 | 5.5 | 5 | 3 | 3 | 0 | 0
217 |  |  | 3 | [5 empty] | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 4.5 | 4.5 | 4.5 | 3.5 | 3.5 | 3 | 1 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Cameron Gagnon | CG |  |  |  |  | CG | 24.1 | 22.1 | 19.1 | 19.1 | 19.1 | 19.1 | 19.1 | 18.6 | 15.1 | 10.6 | 10.6 | 7.1 | 5.1 | 5 | 0 | 0
223 |  | Justin Fan | JF |  |  |  |  | JF | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 11 | 8.5 | 3 | 0
224 |  | Alex Wang | AW |  |  |  |  | AW | 15 | 15 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 3 | 0
225 |  | Stephen Kline | SK |  |  |  |  | SK | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1 | 63.1
236

## Daily Scrum
Producer | 2017-04-21 |  | Team Members
Approved | Dates |  | Cameron Gagnon | Justin Fan | Alex Wang | Stephen Kline | All
| 2017-04-03 | Mon |  |  | Done: Rudimentary Menu system Next: Add polish and juice Help: —
| 2017-04-04 | Tue | Done: UFO's bring in the players when they respawn Next: Have UFO's drop off players in the beginning of the build phase Help: N/A | Done: Swap moved to X Next: Debug swapping | Done: More work on Menu system Next: Inject more juice Help: — |  | Done: Group meetup, discuss and work on this week's sprint stuff Next: Decide on swapping and repairing blocks Help: Moar playtesters for our game and the other teams game
| 2017-04-05 | Wed |  |  | Done: Completed baseline Menu system Next: Get feedback; Connect menu settings to game logic Help: —
| 2017-04-06 | Thu
| 2017-04-07 | Fri |  |  | Done: Got feedback Next: Conect menu settings to game logic Help: —
| 2017-04-08 | Sat
| 2017-04-09 | Sun
| 2017-04-10 | Mon
| 2017-04-11 | Tue | Done: Slow Mo and Screen shake on core destruction; enable green highlight where player can place block; change holding position of item blocks Next: Fix it so players aren't seen when falling off the ship and the camera zooms out; Tweak tutorial so it's more clear how to play Help: -- |  |  | Done: Trailer version 1.0 Next: Leave for 5 days, abandoning my team
| 2017-04-12 | Wed | Done: Fix location where players freeze so that they can't be seen when the UFO picks them up and the screen is zoomed out; Move up and down movement to the left joystick as well. No more Down + A or Left Bumper; Move piloting to RB; Next: Tweak Tutorial screens | Done: Removed input code for jump, swap, repair, helped tweak tutorial Next: Design Expo Help: Brainstorming for Gamma
| 2017-04-13 | Thu | Done: new tutorial; switch to battle phase early Next: Implement feedback from expo Help: -- |  | Done: Got feedback from the expo Next: Finish remaining tasks and address expo feedback Help: —
| 2017-04-14 | Fri
| 2017-04-15 | Sat | Done: Offscreen icon for players; tweak countdown timer to line up when money runs out early; re-add backgrounds to phase manager to give them gravity; Add Another step to tutorial after build phase to make more note of shooting/piloting instructions; Next: Help with new blocks/jelly mode Halp: --- | Done: Started planning justification, prototyped reflector block Next: finish reflector block, ramming mechanic, exploding blocks | Done: Fixed builds with menus Next: Inject mountains of juice Help: —
| 2017-04-16 | Sun | Done: Adding the best feature of the game (jelly mode) Next: Helping out with creating the new blocks Halp: GameManager settings not persisting | Done: Reflector Block prototype Next: Exploding block, ramming mechanic Help: — | Done: Connected Menu logic with game logic; Split main scene into a testing scene and the actual main scene Next: Inject mountains of juice Help: —
| 2017-04-17 | Mon | Done: Make reflector polymorphic; start working on explosive and ramming mechanics Next: finish explosive and ramming mechanics Halp: everything... these mechanics have been buggy to implement. had to reduce the number of layers interacting in Physics2D to get things working better | Done: Exploding block work Next: Exploding block, ramming mechanic, exam tomorrow Help: Exploding block | Done: Playtest and collect gameplay footage Next: Add arrow indicator for players to see their characters better Help: — | Done: Fix bug with # of players not matching # of controllers Next: Work on trailer 2.0 | Done: Playtest and collect gameplay footage Next: Add arrow indicator for players to see their characters better Help: —
| 2017-04-18 | Tue | Done: Replace coin UI with core healthbars during battle phase; finish explosive/ramming mechanics; fix jellymode bug; new explosive sprite Next: add freeze frames to tutorial to showcase block spawners and piloting/battle controls Help: how to have UI not scale with screen size? |  | Done: Arrow indicator; Banner UI; Menu bug fix Next: Space Junk Platforms; Buy Juice Help: — | Done: Get game footage for trailer 2.0 Next: Put it in the trailer
| 2017-04-19 | Wed |  | Done: Damaged block sprites, explosion and crashing sound effects Next: Playtesting, justification document Help: Expos tomorrow and friday! |  | Done: Trailer 2.0 Next: EMU Expo and Showcase
| 2017-04-20 | Thu | Done: Add healthbar back on core as well as corners of screen. Next: 494 showcase Halp: never figured out scaling stuff. hopefully the spotlight feature will provide the same effect | Done: Boundary/downjump/placement restrictions, rocket platform position tweak Next: Playtesting, justification document Help: Scrum, burndown, expo friday! | Done: Tutorial now highlights blocks in middle Next: Space Junk Platforms? Maybe Help: — | Done: EMU Expo (I got a potato) Next: 494 Showcase | EMU Exposition
| 2017-04-21 | Fri |  | Done: Playtesting new tutorial tweaks, justification documents Next: Submission and expo!
| 2017-04-22 | Sat
| 2017-04-23 | Sun
| 2017-04-24 | Mon