## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 54 | 0 |  |  |  | 19 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1
| 3/06 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Wed | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-02-15 | 2/17 | 2/18 | 2/19 | 2/20 | 2/22 | 2/24 | 2/25 | 2/26 | 2/27 | 3/01 | 3/03 | 3/04 | 3/05 | 3/06 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
7 | 1 | Brainstorm ideas for games | ALL |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Verify?
8 | 1 | Research and Analysis Doc (just mark off 2 hours when you finish your 2 pages/games) | ALL |  | 8 | 0 | 5 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 2 | 0 | 0 |  | Fixed
9 | [25 empty] | Deferred
Player | [25 empty] | Reported
11 | 1 | Movement | AW | JF | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | Can't Repro
12 | 1 | Picking up and positioning blocks | AW | JF | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
13 | 1 | Throwing objects | AW |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2 | Controller Input consolidation | AW |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 3 | Spriting and animation | JF | AW | 3 | 0 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Very basic place holders will be enough
15 | 1 | Four player mode | AW |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
15 | 5 | Divide arena into two halves and adjust camera | SK |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Not need for Monday's prototype.
Block Mechanics | [25 empty] | Reported
17 | 1 | Block Placement - Connecting to neighbors | SK |  | 3 | 0 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2 | Block Placement - Guiding the player | JF |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0
19 | 1 | Block destruction/separation | CG | SK | 3 | 0 | 4 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0
20 | 1 | Generic Block | SK |  | 1 | 0 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | Block collision | JF |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
23 | 2 | Block health | CG |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Block Offense
21 | 2 | Weapon Block (actual weapon abilities) | CG |  | 3 | 0 | 4 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0
22 | 1 | Weapon Block (block that represents a weapon) | CG |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Game Manager
26 | 2 | Phase Timer (Disable use of weapons during build phase) | SK |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
27 | 2 | Winning conditions | SK |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
28
29
Environment
34 | 1 | Resource creation | JF |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
27 | 2 | Weapon item (item/resource that represents a weapon block) | CG |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
27 | 2 | Block item (item/resource that represents a block) | CG |  | 1 | 0 | 1.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
35
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
37 | 3 | Block placement currently can be in invalid spot (Can be placed where a previous block is already placed) | ALL |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | Worked around with guidance update, but blocks should be anchored to ground later | Done. Blocks anchored to ground
38
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 19 | 19 | 17 | 16 | 15 | 14 | 12 | 10 | 9 | 8 | 7 | 5 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 54 | 54 | 48.3 | 45.5 | 42.6 | 39.8 | 34.1 | 28.4 | 25.6 | 22.7 | 19.9 | 14.2 | 8.5 | 5.7 | 2.8 | 0.0
212
213 |  | Sum | [6 empty] | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 34 | 30 | 30 | 25 | 25 | 25 | 25 | 22 | 22 | 22 | 22 | 19 | 12 | 9 | 4 | 0
216 |  |  | 2 | [5 empty] | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 11 | 8 | 5 | 1 | 0
217 |  |  | 3 | [5 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Cameron Gagnon | CG |  |  |  |  | CG | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 3 | 0 | 0 | 0
223 |  | Alexander Wang | AW |  |  |  |  | AW | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 4 | 0
224 |  | Stephen Kline | SK |  |  |  |  | SK | 9 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
225 |  | Justin Fan | JF |  |  |  |  | JF | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 8 | 7 | 7 | 4 | 0
226 |  | All | ALL |  |  |  |  | ALL | 15 | 15 | 15 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 7 | 3 | 1 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54 | 54
236

## Daily Scrum
Producer | 3/06 |  | Team Members
Approved | Dates |  | Cameron Gagnon | Alexander Wang | Stephen Kline | Justin Fan | All
| 2/15 | Wed
| 2/16 | Thu
| 2/17 | Fri
| 2/18 | Sat
| 2/19 | Sun
| 2/20 | Mon |  |  |  |  | Done: Threw around ideas for game Next: Finalized game's core mechanics Help: —
| 2/21 | Tue
| 2/22 | Wed |  | Done: Designed Player state chart diagram and code Next: Implement Player Help: — |  |  | Done: Discussed and finalized core game mechanics; Divied up tasks Next: Begin development Help: —
| 2/23 | Thu |  | Done: Implemented half of player Next: Finish player Help: —
| 2/24 | Fri |  | Done: Rudimentary Player script Next: — Help: —
| 2/25 | Sat
| 2/26 | Sun
| 2/27 | Mon |  |  |  | Done: Completed game research and planned out part of R and A Next: Work on block behavior Help: Grid alignment details
| 2/28 | Tue | Done: R&A 2 games Next: Have player spawn blocks instead of a mouseClick
| 3/01 | Wed | Done: Update blocks Next: WeaponItem spawns Help: --
| 3/02 | Thu | Done: Player manning weapons/firing Next: Block health Help: -- |  |  | Done: Block platform colliders for player movement Next: Block spawners, character revamp, four player mode Help: Need to meet with friends
| 3/03 | Fri | Done: Block health Next: check in with everyone Help: --
| 3/04 | Sat |  | Done: Research and Writing of portion of R&A Next: 4 player control; Double checking of player movement with other components Help: — |  | Done: Not much. Some stuff with block collision bug Next: Item spawners and object pooling prototype
| 3/05 | Sun | Done: Blocks can cantilever off edge, projectiles are destroyed on contact Next: -- Help: -- | Done: 3 player controls Next: — Help: — |  | Done: Block spawners and bugtesting, item placement guidance Next: Player movement revamp Help: Scene consolidation and build | Done: Integrated everyone's components together Next: --
| 3/06 | Mon |  |  |  | Done: Player movement, scene consolidation, spawner integration Next: Final build, zip, and ready for submit Help: Waiting on burndown updates
| 3/07 | Tue
| 3/08 | Wed