## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 53.5 | 4 |  |  |  | 14 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 3/13 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2017-03-06 | 3/07 | 3/08 | 3/09 | 3/10 | 3/11 | 3/12 | 3/13 | 3/14 | 3/15 | 3/16 | 3/17 | 3/18 | 3/19 | 3/20 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Brainstorming | ALL |  | 20 | 0 | 7 |  | 20 | 18 | 18 | 16 | 11 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0 |  | Assigned
7 | [25 empty] | Verify?
Guiding the Player | [25 empty] | Reported
9 | 2 | Block tooltips (when near a block show tooltip to pickup block) | JF |  | 1 | 1 |  |  | 1 | 1 | [15 empty] | Deferred | bar: Tue 3/07 to Mon 3/20
6 | 2 | Animation when spending points on block pickup | CG |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | 2 | Flash points red when not enough points to pick up block | CG |  | 1 | 0 | 0.5 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
8 | 2 | Tooltip for placing block (how to aim && place block) | JF |  | 1 | 1 |  |  | 1 | 1 | [15 empty] | Active | bar: Tue 3/07 to Mon 3/20
9 | 2 | Tooltip for down jump | JF |  | 1 | 1 |  |  | 1 | 1 | [15 empty] | Active | bar: Tue 3/07 to Mon 3/20
9 | 2 | Warning before floor drops away (tell them to get on their ship?) | JF |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
11
Player | [25 empty] | Reported
10 | 1 | Player Shooting | AW |  | 2 | 0 | 1.5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | 3 | Grappling Hook | AW |  | 3 | 1 | 2 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | Can't Repro
12 | 1 | Down Jump | JF |  | 3 | 0 | 2 |  | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 3 | Player Respriting and Animation | JF |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
Blocks | [25 empty] | Reported
13 | 1 | Remove joint on death (destroy when offscreen) | CG |  | 2 | 0 | 3 |  | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Blocks of different healths | CG |  | 1 | 0 | 0.5 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 1 | Block dispensers | JF |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16
Phases
18 | 1 | Remove ground at start of battle phase | SK |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2 | Background to show movement | SK |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 1 | End when core is destroyed | SK |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Phase length tuning | JF |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 1 | End if one team falls off rocket | JF |  | 1 | 0 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23
Environment/Resources | [25 empty] | Reported
26 | 1 | Resource spending | CG |  | 1.5 | 0 | 1.5 |  | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 1 | Core (1x1) | SK |  | 2 | 0 |  |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27
28
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | [25 empty] | Reported
108 | [25 empty] | Reported
109 | [25 empty] | Reported
110 | [25 empty] | Reported
111 | [25 empty] | Reported
112 | [25 empty] | Reported
113 | [25 empty] | Reported
114 | [25 empty] | Reported
115 | [25 empty] | Reported
116 | [25 empty] | Reported
117 | [25 empty] | Reported
118 | [25 empty] | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 14 | 14 | 13 | 12 | 11 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3 | 2 | 1 | 0
211 |  | Optimum | [5 empty] | Line | 53.5 | 53.5 | 49.7 | 45.9 | 42.0 | 38.2 | 34.4 | 30.6 | 26.8 | 22.9 | 19.1 | 15.3 | 11.5 | 7.6 | 3.8 | 0.0
212
213 |  | Sum | [6 empty] | 51.5 | 51.5 | 51.5 | 51.5 | 51.5 | 51.5 | 51.5 | 51.5 | 51.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 38.5 | 36.5 | 36.5 | 34.5 | 23 | 19 | 19 | 10 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0
216 |  |  | 2 | [5 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 6.5 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
217 |  |  | 3 | [5 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Cameron Gagnon | CG |  |  |  |  | CG | 6.5 | 6.5 | 6.5 | 6.5 | 4 | 2 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 |  | Alexander Wang | AW |  |  |  |  | AW | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
224 |  | Stephen Kline | SK |  |  |  |  | SK | 6 | 6 | 6 | 6 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 |  | Justin Fan | JF |  |  |  |  | JF | 16 | 16 | 16 | 16 | 13 | 13 | 13 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
226 |  | All | ALL |  |  |  |  | ALL | 20 | 18 | 18 | 16 | 11 | 11 | 11 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 | 53.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236

## Daily Scrum
Producer | 3/13 |  | Team Members
Approved | Dates |  | Cameron Gagnon | Alexander Wang | Stephen Kline | Justin Fan | All
| 3/06 | Mon | Done: Brainstorm Next: Brainstorm Help: — | Done: Brainstorm Next: Brainstorm Help: — | Done: Brainstorm Next: Continue brainstorming | Recover from prototype | Done: Brainstorm Next: Brainstorm Help: —
| 3/07 | Tue | Done: Brainstorm Next: Brainstorm Help: — | Done: — Next: Brainstorm Help: — | Done: Brainstorm Next: N/A | Done: Brainstorm Next: Brainstorm Help: — | Done: Brainstorm Next: Brainstorm Help: —
| 3/08 | Wed | Done: Brainstorm Next: Brainstorm Help: — | Done: Brainstorm; Talked with Austin Next: Brainstorm Help: — | Done: Talk through ideas with Austin Next: Finalize new mechanic ideas | Sick | Done: Brainstormed with Austin Next: Final brainstorm for alpha Help: being game designers
| 3/09 | Thu | Done: Brainstorm Next: Various health levels to blocks Help: -- | Done: Brainstorm; Talked with Austin; Next: Player shooting Help: — | Done: Finalize brainstorming Next: Remove ground at start of round, make engines and core | Done: Player movement improvements, platform tweaks, control scheme revamp v2 Next: Resource creation and assets | Done: Finalize basic alpha features Next: Begin development for alpha Help: —
| 3/10 | Fri | Done: health levels && blocks unhinging && point/spending system Next: Tooltip/guiding the player for point system |  | Done: Make engines and core and move ground Next: Add background
| 3/11 | Sat |  | Done: Player Aiming Next: Player shooting Help: — | Done: Tweaked core and engines Next: Add background
| 3/12 | Sun |  | Done: Player Shooting Next: Grappling Hook Help: — |  | Done: Resource creation tweaks, conveyor belt setting, phase adjustments Next: Tutorial tooltips and player respriting
| 3/13 | Mon |  |  |  | Done: Player control scheme tweaks, player respriting, players falling off lose conditon Next: Tutorial tooltips
| 3/14 | Tue
| 3/15 | Wed
| 3/16 | Thu
| 3/17 | Fri
| 3/18 | Sat
| 3/19 | Sun
| 3/20 | Mon
| 3/21 | Tue
| 3/22 | Wed
| 3/23 | Thu
| 3/24 | Fri
| 3/25 | Sat
| 3/26 | Sun
| 3/27 | Mon